## Project checklist
SAMPLE · The project and the 12 tasks in rows 9–20 are fictional. Type over them or delete them. Instructions: “How to use” tab.
Project checklist
| Project | Website relaunch: Juniper Yoga Loft |  |  | Progress
| Owner | Sam Ortiz
| Start date | 2026-09-28
| Deadline | 2026-11-20
Days left
# | Task | Phase | Owner | Due date | Status | Notes
| Kick-off call and goals | Planning | Sam | 2026-09-29 | Done | Sample
| List pages and features | Planning | Sam | 2026-10-02 | Done | Sample
| Collect photos and logo files | Content | Ava | 2026-10-06 | Done | Sample
| Write home and class pages | Content | Ava | 2026-10-09 | In progress | Sample
| Choose the booking tool | Build | Sam | 2026-10-12 | Blocked | Sample · Waiting for prices from 2 vendors
| Design the home page | Build | Noah | 2026-10-16 | In progress | Sample
| Build the remaining pages | Build | Noah | 2026-10-30 | To do | Sample
| Set up contact form and e-mails | Build | Noah | 2026-11-03 | To do | Sample
| Test on phone and desktop | Launch | Ava | 2026-11-10 | To do | Sample
| Connect the domain | Launch | Sam | 2026-11-16 | To do | Sample
| Announce to members | Launch | Ava | 2026-11-20 | To do | Sample
| Review traffic after 2 weeks | Review | Sam | 2026-12-04 | To do | Sample
Formulas:
Website relaunch: Juniper Yoga Loft = IF([Website relaunch: Juniper Yoga Loft, row above]="","",[Website relaunch: Juniper Yoga Loft, row above]-TODAY())

## Meeting checklist
SAMPLE · The meeting, agenda and action items are fictional. Type over them. Instructions: “How to use” tab.
Meeting checklist
| Meeting | Monthly team meeting
| Date | 2026-10-20
| Start time | 9:30
| Where / link | Studio B + video call
Ends at (from the agenda)
BEFORE THE MEETING
Done | Item | Who
✓ | Write the goal of the meeting in one sentence | Maya
✓ | Send the agenda 24 h before | Maya
✓ | Book the room and share the video link | Owen
| Prepare the figures for item 2 | Priya
| Invite only the people needed | Maya
| Pick a note-taker | Maya
AGENDA
Starts | Topic | Lead | Minutes
| Wins of the month | Maya | 10
| Sales and bookings: figures | Priya | 15
| New menu: feedback | Jonah | 15
| Schedule for the holidays | Maya | 10
| Questions | All | 10
Total
ACTION ITEMS
# | Action | Owner | Due date | Status | Notes
| Send the holiday schedule | Maya | 2026-10-23 | In progress | Sample
| Order the new menu cards | Jonah | 2026-10-27 | To do | Sample
| Share bookings report every Monday | Priya | 2026-10-26 | To do | Sample

## How to use
Project & meeting checklist: how to use it
Two simple checklists: one to keep a project on track (tasks, owners, due dates, progress), one to run a meeting (preparation, timed agenda, action items).
Quick start
1. | Project tab: type the project name, owner, start date and deadline. “Days left” counts down on its own.
2. | Replace the 12 sample tasks with yours (one per row, up to 40). Pick a phase, write who does it and when.
3. | Update the Status as you go: Done tasks are crossed out, Blocked ones turn red, late ones show their date in orange.
4. | The progress bar at the top shows how much is done.
5. | Meeting tab: tick the preparation items with ✓, write the agenda with minutes per topic: start times and the end time calculate on their own.
6. | During the meeting, write the action items with an owner and a due date. Print it or save it as PDF to share.
Good to know
• | Use the filter arrows in the header to show one phase, one owner or only what’s left to do.
• | Need a new checklist? Right-click the tab → Move or Copy → Create a copy.
• | White cells are yours to fill in. Cells with a grey background, and columns with a grey header, calculate on their own: don’t type over them.
• | Cells with a drop-down show a small arrow when you select them. To change the choices: Data → Data Validation (Google Sheets: Data → Data validation).
• | Works in Excel (Windows, Mac, web) and Apple Numbers. For Google Sheets, download the Google Sheets copy from the same page.
Sample data
The project, the 12 tasks (rows 9–20), the meeting, its agenda and action items are fictional examples. Type over them or delete them.
Want it automated for your business?
Dashboard, alerts, macros, connected to your data: we build the custom version for you. For example: all your projects in one dashboard with progress and workload per person, deadline alerts by e-mail, a timeline view.
→ Excel or Google Sheets dashboard · from $149 · 2-day delivery
Free template by Allset Studio · https://theallsetstudio.pages.dev/templates/ · free to use in your business.